## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP)
State: | Adamawa
Reporting period: |  | FY 2025
SABER Focal Person: |  | Dr. Bello Abubakar Song
Was this plan prepared in consultation with the Private Sector |  |  |  | Yes
List of contributing entities: |  |  | 1 Ministry of Finance
2. Ministry of Budget & Economic Planning
3. Ministry of Commerce, Trade & Industry
4. Ministry of Justice
5. Ministry of Environment
6. Ministry of Lands & Survey
7. Ministry of Information and Strategy
8. Ministry of Enterprenuership Development
9. Adamawa State Geographic Information System (ADGIS)
10. Adamawa State Urban and Regional Development Board
11. Adamawa State Board of Internal Revenue (ASBIR)
12. Adamawa State Fiscal Responsibility Commission
13. Adamawa State Planning Commission
14. Office of the Surveyor General Adamawa State (OSGAS)
15. Adamawa State Bureau of Statistics
16. Adamawa State Investment and Property Development Company
17. Adamawa State Information Technology Development Agency (ASITDA)
18. Adamawa State Chamber of Commerce, Industry, Mines, and Agriculture (ADCCIMA)
19. Adamawa State House of Assembly
20. Adamawa State Judiciary
URL Link to the published BERAP |  |  | www.saber.adamawastate.gov.ng
Is this plan approved by the State Executive Council (SEC) |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  |  | 2024-12-18
Please further to proof of private sector consultation, please include for the purpose of the Verification Protocol: (a) summary of private sector consultation, and (b) list of private sector participants invited to the consultation – including name, organization, designation of representative, phone number and email address and other information as may be deemed relevant

## BERAP
BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) TEMPLATE
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | List of Private Sector contributors | Estimated costs | Planned Start Date | Planned End Date
1 | Improve efficiency in property registration and sustainability of Land base investment process | To improve transparency and accountability of Land System Administration in the state. | i. Review the legal and regulatory procedures, parameters, and purposes for land acquisition as well as conversion of land ownership. ii. Comply with Environmental, Safety Management, procedures with relevant MDS on the Land Use • ADSG will simplify the land application and allocation process using our two electronic platform lms.adamawastate.gov.ng for application and allocation of land in Adamawa State. • ADSG will create 200 plots of 10 hectares each and make available to investors in 2025 to enhance food security under the FRILIA Framework. • ADSG will allocate land for the Adamawa Digital Park for the development of ICT Innovation in Yola North, Mubi and Numan. • The Government will conclude the implementation of SLTR in 2025 targetting conversions of customary titles and issuing CofO’s • ADSG will allocate new layouts for individual and corporate 100% electronic in 2025. | To improve investors' awareness on requirements and procedures for land administration system in Adamawa State 100% implementation in 2025 | General Public, Individuals, Investors,and corporate organizations. | Ministry of Land and Survey (Adamawa State Geopgraphical Information System (ADGIS) and Office Surveyor General Adamawa State (OSGAS)) | Adamawa State Board of Internal Revenue, Adamawa State Urban and Regional Development Board | i. Adamawa Chamber of Commerce,Industry,Mines and Agriculture ii. Manufacturers Ass. Of Nigeria iii. Nigeria Association of Small-scale Industrialist iv. Nigeria Association Ass. Of Small & medium Ent. v. Shippers Ass. Of Nigeria-Adamawa Chapter vi. Real Estate Agents Association vii. Real Estate Surveyors & Valuers. | N100M | 22nd January, 2025 | 30th August, 2025
2 | IMPROVED REGULATORY FRAMEWORK FOR PRIVATE INVESTMENT IN FIBER OPTIC INFRASTRUCTURE DIGITALLY | To Provide friendly environment to attract new business in fiber optics infrastructure in the state. | i. Constitution of State Technical Team to be drawn from relevant Stakeholders (Public & private) to oversee process implementation ii. Attract investment into fiber optics. iii. Improve broad connectivity along the newly constructed roads in the state by deploying Fiber Optic Cables. iv. Publish on the state official website: Approved ROW-related requests by operators.• To connect 100 public schools to the Giga Fiber optic infrastructure • To connect 100 Hospitals/PHC’s covering all senatorial districts Giga Fiber optic infrastructure • To connect public offices in all senatorial zones to the Giga Fiber optic infrastructure | i. To provide friendly environment to attract new businesses/investments in fibre optic infrastructure development in the State. ii. To simplify the processes of obtaining the Right of Way (RoW) in Fiber Optic Deployment | Telecom service provider, ICT and Future Artificial Inteligence (AI) Services | Ministry of Information and Strategy, Adamawa State Information Technology Development Agency (ASITDA) | Ministry of Land & Survey, Adamawa State Board of Internal Revenue, Adamawa State Urban Planning Development Authority | i. Adamawa Chamber of Commerce,Industry,Mines and Agriculture ii. Manufacturers Ass. Of Nigeria iii. Nigeria Association of Small-scale Industrialist iv. Nigeria Association Ass. Of Small & medium Ent. v. Shippers Ass. Of Nigeria-Adamawa Chapter vi. Real Estate Agents Association vii. Real Estate Surveyors & Valuers. | N100M | 22nd January, 2025 | 22nd Nov 2025
3 | Development of an effective PPP framework | Attract suitable and sustainable large-scale PPP projects to Adamawa State | I. Development of PPP Fiscal Commitment and Contingent Liability (FCCL) Management Framework. II. PPP Legal and Institutional framework. III. PPP Disclosure Framework IV. Establishment of state project facilitation fund | i. To increase new businesses/investments opportunities in the State by 30% using 2022 as a baseline to enhance GDP growth ii. Increase the number of SMEs accessing credit facilities in the State by 30% From 2022 – 2025 | Investors, SMEs | Ministry of Finance, Adamawa State Planning Commision, Ministry of Commerce,Trade and Industry, Ministry of Enterprenuership Development, Ministry of Agriculture, Adamawa State Investment Promotion Unit | Adamawa State Investment Promotion Unit, Adamawa State Poverty Alleviation and Wealth Creation Agency (PAWECA), Ministry of Women Affairs, Ministry of Youth and Sports | i. Adamawa Chamber of Commerce,Industry,Mines and Agriculture ii. Manufacturers Ass. Of Nigeria iii. Nigeria Association of Small-scale Industrialist iv. Nigeria Association Ass. Of Small & medium Ent. v. Shippers Ass. Of Nigeria-Adamawa Chapter vi. Real Estate Agents Association vii. Real Estate Surveyors & Valuers. | N150M | 23rd January, 2025 | 25th Nov 2025
4 | INCREASED INVESTMENT PROMOTION ENVIRONMENT | To provide an enabling investment environment to the state. | I. Update the investor tracking system. II. Provision of relevant services to investors through a comprehensive investor service framework.To partner CAC to create a one-stop shp for business registration in the areas of renewable energy, Information Communications Technology and Solid Minerals, Agriculture and Tourism. ADSG will target 20 Companies per month and 240 per year in 2025. ADSG will link SME’s and Big Businesses with the AFCTA market in 2025 to add value and export agriproducts and BPO services across the continent. | To increase new business/investmennt in the state to enhance the growth & GDP | Investors, SMEs | Ministry of Finance, Adamawa State Planning Commision, Ministry of Commerce,Trade and Industry, Ministry of Enterprenuership Development, Ministry of Agriculture, Adamawa State Investment Promotion Unit | Adamawa State Investment Promotion Unit, Adamawa State Poverty Alleviation and Wealth Creation Agency (PAWECA), Ministry of Women Affairs, Ministry of Youth and Sports | i. Adamawa Chamber of Commerce,Industry,Mines and Agriculture ii. Manufacturers Ass. Of Nigeria iii. Nigeria Association of Small-scale Industrialist iv. Nigeria Association Ass. Of Small & medium Ent. v. Shippers Ass. Of Nigeria-Adamawa Chapter vi. Real Estate Agents Association vii. Real Estate Surveyors & Valuers. | N150M | 23rd January, 2025 | 25th Nov 2025
5 | INCREASED TRANSPARENCY OF OFFICIAL FEES AND PROCEDURES | Increase transparency of official fees and procedure on the 5 business enabling environemtn MDAs | i. Finalize the process of obtaining business premises registration permit in the ministry of Commerce. ii. Finalize the process of obtaining road worthiness in the road traffic department (VIO) ministry of transport. iii. Finalize the process of obtaining signage and advertisement from Adamawa State Urban Planning and Development Board. iv. Finalize the process of obtaining water connection from Adamawa State waterboard v. Finalize the process of obtaining Environmental impact assessment (IEA Report) from Adamawa State Environmental Protection Agency. | Business Regulatory process mapping signed off by all MDAs and Approved by relevant authorities. | SMEs, Contractors, Women Organisaition and NGOs | Adamawa State Revenue Board through the grievance redress mechanism | Adamawa State Ministry of Finance, Adamawa state boardinternal reveneu, Water Biard, ASUPDA, Ministry of transport, Minitry of Commerce, Ministry of environment | Road Transport workerks, Civil Engineers, Adamawa State Chamber of Commerce, Environmentalist, and Association of advertisement. | N100M | 22nd January, 2025 | 20th December, 2025
6 | INCREASED TRANSPARENCY OF FEES AND LEVIES FOR INTER-STATE TRADE AND INCREASED EXPORT CERTIFICATION | To improve transparency and justification for fees and levies with a view to enhancing revenue and traders confidence in the state | I. To compile and publish fees and levies etc (other than taxes) on the State Official Website. II. Provision of hotline /SMS for receiving feedback and reports. III. Increase number of firms in the state that obtain export certificates from NEPC by at least 20% from the baseline year (2021). IV. Publish on state official website(s): fees, procedures, and service delivery timelines of five key BEE State MDAs V. Issue State Executive Order to direct five State BEE MDAs to publish on state official website(s) their fees, procedures, Service Level Agreements (SLAs), Grievance Redress Mechanism (GRM), and mandatory advance communication rules of upcoming changes, as per the verification protocols. VI. Operationalize GRMs for at least two key BEE State MDAs and address a minimum of 50% of grievances received within the specified SLAs. VII. Publish on state official website: schedule of trade related fees and levies on inter-state movement of goods; VIII. Establish GRM for traders including SMS/hotline for reporting and redress IX. Publish on state website report on complaints from traders and redress actions; X. Address a minimum of 75 percent of grievances received in the Grievance Redress Mechanism (GRM) within the specified SLAs. | i. To have transparent fees, charges or levies in order to improve payments on Inter-State trade. ii. To establish GRM for traders including SMEs and hotline for reporting and redress. iii. Publish on official website state export strategy and guidelines• ADSG to register and enable 100 exporters in 2025 • To resolve all grievances across all sectors 100% electronically | Exporters and Traders | Ministry of Commerce, Trade and Industry, Adamawa State Board of Internal Revenue | Ministry of Agriculture, Ministry of Livestock, Ministry of Environment | i. Adamawa Chamber of Commerce,Industry,Mines and Agriculture ii. Manufacturers Ass. Of Nigeria iii. Nigeria Association of Small-scale Industrialist iv. Nigeria Association Ass. Of Small & medium Ent. v. Shippers Ass. Of Nigeria-Adamawa Chapter vi. Real Estate Agents Association vii. Real Estate Surveyors & Valuers. | N100M | 22nd January, 2025 | 20th December, 2025
7 | SIMPLIFY STATE AND LOCAL BUSINESS TAX REGIMES | To harmonise state and local government revenue into a single consolidated demand notice and electronic payment platform for transparency. | I. Amend the state revenue law to adopt presumptive tax regime for small businesses. II. To subsume business related local government charges/fees/Taxes into a consolidated demand notice. III. Electronic Payment with e-receipt generation and QR Code for unique payment.• ADSG will begin the implementation of the new amended revenue law 2024 in 2025 • ADSG will transition 100% taxes and receipts via payments.adamawastate.gov.ng • Expansion of the harmonised LGA revenue from the initial 3 LGA’s to 21 LGA’s in 2025. | I. ammended laws approved by the house of assembly are uploaded to the state website. II. Fully automate IGR collection process. | SMEs/Investors | Adamawa State internal revenue, | Ministry of Finance, Ministry of Budget and planning, Adamawa State Planning commision, ministy of justice, ministry for local government affairs. | Adamawa State Chamber of Commerce | N100M | 22nd January, 2025 | 20th December, 2025
8 | QUICK DETERMINATION OF COMMERCIAL DISPUTES | To create harmonious business and commercial activity in the state through quick dispensation of commercial desputes. | i. Capacity Building for Judges of the Small Claims Courts. ii. Capacity Building for court officials. iii. Sensitization workshops for organized private sector on the operational guideline of the small claims courts iv. Published on State judiciary website: Monthly Performance Report of the small claims courts; | Reduce number of days for handling of commercial cases by 30% 2024-2025 | SMEs | Adamawa State Judiciary/ Ministry of Justice | Ministry of Justice, Adamawa State High Court, Ministtry of Finance, Ministry of Budget and Planning, Adamawa State Planning Commison & Adamawa State House of assembly. | i. Adamawa Chamber of Commerce,Industry,Mines and Agriculture ii. Manufacturers Ass. Of Nigeria iii. Nigeria Association of Small-scale Industrialist iv. Nigeria Association Ass. Of Small & medium Ent. v. Shippers Ass. Of Nigeria-Adamawa Chapter vi. Real Estate Agents Association vii. Real Estate Surveyors & Valuers. | N200M | 22nd January, 2025 | 22nd Nov. 2025

## Progress Report (hidden)
BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
| The focus area for the reforms eg transparency of official fees and procedures | What the State intends to achieve by implementing the Business Enabling Reform | Very detailed, step by step process on how the objective will be achieved | User, beneficiaries, recipient of the reform Explain actions and/or sub-actions and include targets | One MDA responsible for the action/activity | Supporting MDAs | Estimated budget for the action/activity | When you commit to start the implementation of the actions | When you commit to complete the actions and achieve tour targets | Indicate whether the action/activity is completed, ongoing - on time, ongoing - delayed or dropped | Describe the status of each action, explaining reasons for any delays or actions being dropped. Explain any changes that occurred during implementation affecting start and end dates | Describe next steps for the outstanding actions. For example, is the action getting carried over to the following year's action plan?
1 | Illustrative example: Transparency of official fees and procedures | Illustrative example: This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs | Illustrative example A. Finalise process mapping of one business regulatory area number 1 | A description of the action and target, e.g. business regulatory process mapping signed off by all included MDAs and approved by the relevant authority | List the one MDA that would be responsible for this action/activity | List the several MDAs that would actively contribute to the activity | Amount (in Naira) | Day, Month, Year | Day, Month, Year
Illustrative example A.1. Map existing process for carrying out impact evaluation
B.
B.1
B.2
C.
C.1
C.2